Implementation Timeline and Risk Register

Supporting Document | Week 1

Prepared by
Ruchi Ambatkar

Prepared: October 2026

# Purpose

This supporting document provides a working schedule, milestone gates, and a risk register for the proposed 12-month ML agribusiness programme. The schedule is a planning proposal and should be adjusted to the crop calendar and local operating conditions.

# 12-Month Timeline

| Month | Focus | Key tasks | Deliverable / approval |
| --- | --- | --- | --- |
| 1 | Discovery | Stakeholder interviews, choose crop/region, map decisions | Project charter and scope sign-off |
| 2 | Data audit | Inventory sources, ownership, permission, completeness | Data inventory and quality report |
| 3 | Data preparation | Clean, standardize, define data dictionary and access rules | Approved data-readiness gate |
| 4 | Baseline | Define metrics and splits; create simple baseline | Baseline and validation plan |
| 5 | Model build | Train candidate yield/risk models | Candidate model comparison |
| 6 | Prototype | Dashboard/SMS mock-up; usability and security review | Prototype and model card |
| 7 | Pilot preparation | Train users, define fallback and incident route | Pilot readiness checklist |
| 8 | Pilot | Run pilot, log predictions, actions, feedback and incidents | Pilot activity report |
| 9 | Monitoring | Review errors, data drift, adoption and subgroup results | Interim evaluation |
| 10 | Impact review | Compare outcomes and costs against baseline/comparison | Impact and cost-benefit report |
| 11 | Scale planning | Plan support, integration, budget and ownership | Deployment roadmap |
| 12 | Decision | Present evidence, lessons, residual risks | Scale / revise / stop decision |

# Risk Register

| ID | Risk | Initial rating | Mitigation | Owner | Trigger for escalation |
| --- | --- | --- | --- | --- | --- |
| R1 | Poor or incomplete data | High | Data profiling; quality gates; record gaps | Data Lead | Key variables missing or unreliable |
| R2 | Unusual weather / changing climate | High | Seasonal validation; uncertainty; monitoring | Agronomy Lead | Error rises materially in current season |
| R3 | Unequal model performance | High | Evaluate by crop, region, farm size; local review | ML Lead | Subgroup errors exceed agreed tolerance |
| R4 | Low adoption | High | Co-design, local language, training, feedback | Field Lead | Usage or action rate below target |
| R5 | Wrong high-impact advice | High | Expert review, thresholds, fallback, audit trail | Agronomy Lead | Any serious adverse outcome |
| R6 | Privacy breach / unauthorized use | High | Data minimization, role access, retention, response plan | Data Owner | Any suspected exposure or complaint |
| R7 | Connectivity failure | Medium | SMS/voice fallback, low-bandwidth workflow | IT Lead | Advisory delivery repeatedly delayed |
| R8 | Cybersecurity incident | High | Updates, access controls, backups, logs | IT Lead | Suspicious access or service compromise |
| R9 | Budget overrun | High | Stage-gated funding, cost tracking, stop criteria | Sponsor/Finance | Spend exceeds approved tolerance |
| R10 | Maintenance/skills gap | Medium | Named owner, runbooks, training and support budget | Programme Lead | No owner or funding for ongoing operation |

# Risk Scoring

Score each risk from 1 to 5 for likelihood and impact. Multiply the two scores. Suggested thresholds: 15–25 = immediate action and sponsor review; 8–14 = documented mitigation and monthly review; 1–7 = routine monitoring. Safety, privacy, and legal risks must be escalated even if a numerical score is low.

# Pilot Decision Gates

Gate 1 — Data: permissions and minimum data quality confirmed.

Gate 2 — Model: validation results meet a pre-agreed threshold and are better than or operationally useful compared with the baseline.

Gate 3 — Safety/usability: agronomy review, user training, fallback channel and incident route are ready.

Gate 4 — Impact: adoption, operational outcome, cost, and subgroup performance reviewed.

Gate 5 — Scale: sponsor approves only if expected benefits, maintenance capacity, and risk controls are credible.